|  |
| --- |
| **Goal*: Skilled Teachers*** *In one year, TCMS teachers will be able to teach/use online student submissions to grade at least 3 online assignments per grading period using Google Classrooms, etc.*  |
| Evaluation Method: Work samplesLesson plans | Success Indicator: By 5/30/17, TCMS teachers will have graded at least 3 online assignments.  |
| Strategies | Timeline | Budget/Funding Source | Person(s) Responsible |
| * Professional development on grading online assignments
 | * 1/2/2017, during the technology day.
 | * None, teacher workday
 | * Administrators
* Teachers who will teach technology classes.
 |
| * Lesson plans and work samples turned in to administrators.
 | * At the end of 3rd Nine Weeks, 3/30/17
 | * None
 | * Teachers
* Administrators
 |
| **Goal: *Instructional Change****In one year, TCMS teachers will be able to use Chromebooks for instructional research or activities 2 times per week (this does not count “free” time on Chromebooks or early finisher assignments).* |
| Evaluation Method: Work samplesLesson plansClassroom observations | Success Indicator: By 5/30/17, TCMS teachers will have used Chromebooks at least 2 times each week as proven by lesson plans and student work samples.  |
| Strategies | Timeline | Budget/Funding Source | Person(s) Responsible |
| * Professional development on research based activities with Chromebooks
 | * 1/2/2017, during the technology day.
 | * None, teacher workday
 | * Administrators
* Teachers who will teach technology classes.
 |
| * Administrators will conduct classroom observations
 | * 1/3/17-3/30/17
 | * None
 | * Administrators
 |
| * Lesson plans and work samples turned in to administrators.
 | * At the end of 3rd Nine Weeks, 3/30/17
 | * None
 | * Teachers
* Administrators
 |
| **Goal: *Student Focused****In one year, TCMS teachers will have technology standards posted at all times to help guide technology lessons.*  |
| Evaluation Method: Classroom Observations | Success Indicator: By 11/1/17, all TCMS teachers will have technology standards posted in their classrooms.  |
| Strategies | Timeline | Budget/Funding Source | Person(s) Responsible |
| * Technology standards will be printed on cardstock.
 | * Before school starts by 7/30/17
 | * None, done on campus
 | * Administration
* Technology Team
 |
| * Technology standards will be passed out to teachers.
 | * 8/15/17
 | * None
 | * Technology Team
 |
| * Classroom observations
 | * 9/1-11/1/17
 | * None
 | * Administration
 |
| **Goal: *Diversity Considerations****In one year, TCMS teachers will nominate students from different diversities (low SES, female, and other ethnic backgrounds) that may need more help or exposure to technology for a special afterschool program.*  |
| Evaluation Method: Teacher submissionsStudent participation (attendance) | Success Indicator: By September 30, 2017, teams (groups of 4 teachers) will nominate students for afterschool program- “Techies.” 15 students will be chosen based on needs and resources available to them at home. The Technology Team will take volunteers to head the program. |
| Strategies | Timeline | Budget/Funding Source | Person(s) Responsible |
| * Teachers volunteer to be “Techie” instructors
 | * By 9/15/17
 | * None
 | * Teachers
* “Techie” Team
 |
| * Teams submit student nominations
 | * By 9/30/17
 | * None
 | * Teachers
* “Techie” Team
 |
| * Nominations are considered and 15 students are chosen
 | * By 10/15/17
 | * None, unless done during school day (sub cost= $80/day)
 | * “Techie” Team
 |
| * “Techie” program begins targeting students with diverse backgrounds.
 | * One hour weekly on Thursdays
 | * Cost of teacher in afterschool program
 | * “Techie” Team
 |
| **Goal: *School Related****In one year, TCMS administrators and educators will have a technology plan that is updated and current available for the district’s website.*  |
| Evaluation Method: * Technology team notes
* Website submission
 | Success Indicator: By 5/30/17, the TCMS Technology Team will have submitted and uploaded a total, updated Technology Plan. |
| Strategies | Timeline | Budget/Funding Source | Person(s) Responsible |
| * Technology team meeting to discuss former technology plan.
 | * One afternoon in the 1st Nine Weeks of school
 | * None
 | * Administration (scheduling)
* Technology Team
 |
| * Technology team meeting to discuss changes.
 | * One afternoon 2nd Nine Weeks of school, before Winter Break
 | * None
 | * Administration (scheduling)
* Technology Team
 |
| * Technology team meeting to discuss rough draft and write final draft.
 | * One afternoon 3rd Nine Weeks of school, before Spring Break
 | * None
 | * Administration (scheduling)
* Technology Team
 |