|  |  |  |  |
| --- | --- | --- | --- |
| **Goal*: Skilled Teachers***  *In one year, TCMS teachers will be able to teach/use online student submissions to grade at least 3 online assignments per grading period using Google Classrooms, etc.* | | | |
| Evaluation Method:  Work samples  Lesson plans | | Success Indicator:  By 5/30/17, TCMS teachers will have graded at least 3 online assignments. | |
| Strategies | Timeline | Budget/Funding Source | Person(s) Responsible |
| * Professional development on grading online assignments | * 1/2/2017, during the technology day. | * None, teacher workday | * Administrators * Teachers who will teach technology classes. |
| * Lesson plans and work samples turned in to administrators. | * At the end of 3rd Nine Weeks, 3/30/17 | * None | * Teachers * Administrators |
| **Goal: *Instructional Change***  *In one year, TCMS teachers will be able to use Chromebooks for instructional research or activities 2 times per week (this does not count “free” time on Chromebooks or early finisher assignments).* | | | |
| Evaluation Method:  Work samples  Lesson plans  Classroom observations | | Success Indicator:  By 5/30/17, TCMS teachers will have used Chromebooks at least 2 times each week as proven by lesson plans and student work samples. | |
| Strategies | Timeline | Budget/Funding Source | Person(s) Responsible |
| * Professional development on research based activities with Chromebooks | * 1/2/2017, during the technology day. | * None, teacher workday | * Administrators * Teachers who will teach technology classes. |
| * Administrators will conduct classroom observations | * 1/3/17-3/30/17 | * None | * Administrators |
| * Lesson plans and work samples turned in to administrators. | * At the end of 3rd Nine Weeks, 3/30/17 | * None | * Teachers * Administrators |
| **Goal: *Student Focused***  *In one year, TCMS teachers will have technology standards posted at all times to help guide technology lessons.* | | | |
| Evaluation Method:  Classroom Observations | | Success Indicator:  By 11/1/17, all TCMS teachers will have technology standards posted in their classrooms. | |
| Strategies | Timeline | Budget/Funding Source | Person(s) Responsible |
| * Technology standards will be printed on cardstock. | * Before school starts by 7/30/17 | * None, done on campus | * Administration * Technology Team |
| * Technology standards will be passed out to teachers. | * 8/15/17 | * None | * Technology Team |
| * Classroom observations | * 9/1-11/1/17 | * None | * Administration |
| **Goal: *Diversity Considerations***  *In one year, TCMS teachers will nominate students from different diversities (low SES, female, and other ethnic backgrounds) that may need more help or exposure to technology for a special afterschool program.* | | | |
| Evaluation Method:  Teacher submissions  Student participation (attendance) | | Success Indicator:  By September 30, 2017, teams (groups of 4 teachers) will nominate students for afterschool program- “Techies.” 15 students will be chosen based on needs and resources available to them at home. The Technology Team will take volunteers to head the program. | |
| Strategies | Timeline | Budget/Funding Source | Person(s) Responsible |
| * Teachers volunteer to be “Techie” instructors | * By 9/15/17 | * None | * Teachers * “Techie” Team |
| * Teams submit student nominations | * By 9/30/17 | * None | * Teachers * “Techie” Team |
| * Nominations are considered and 15 students are chosen | * By 10/15/17 | * None, unless done during school day (sub cost= $80/day) | * “Techie” Team |
| * “Techie” program begins targeting students with diverse backgrounds. | * One hour weekly on Thursdays | * Cost of teacher in afterschool program | * “Techie” Team |
| **Goal: *School Related***  *In one year, TCMS administrators and educators will have a technology plan that is updated and current available for the district’s website.* | | | |
| Evaluation Method:   * Technology team notes * Website submission | | Success Indicator:  By 5/30/17, the TCMS Technology Team will have submitted and uploaded a total, updated Technology Plan. | |
| Strategies | Timeline | Budget/Funding Source | Person(s) Responsible |
| * Technology team meeting to discuss former technology plan. | * One afternoon in the 1st Nine Weeks of school | * None | * Administration (scheduling) * Technology Team |
| * Technology team meeting to discuss changes. | * One afternoon 2nd Nine Weeks of school, before Winter Break | * None | * Administration (scheduling) * Technology Team |
| * Technology team meeting to discuss rough draft and write final draft. | * One afternoon 3rd Nine Weeks of school, before Spring Break | * None | * Administration (scheduling) * Technology Team |